MARSHFIELD AREA HABITAT FOR HUMANITY

KUSAY FAMILY 2019 BUILD SCHEDULE

301 N. JUNO

DATE TASK VOLUNTEERS NEEDED

Saturday, June 25 GROUNDBREAKING Habitat Board, Family,

 Guests

July 27-August 5 Basement and garage foundation Weilers, Reigels Plumbing underfloor, stub water

 and sewer

August 6-12 Floor trusses, floor, headers, Build Com. +

 and stair steps

August 13 (Saturday) Build outside/interior walls 15-20

Aug. 17 (Wednesday) Finish/prep work 5-8

Aug. 20 (Saturday) Garage walls, roof trusses, sheeting. 15-20

Aug. 24 (Wednesday) Finish/prep work Build Com.

Aug. 27 (Saturday) Finish roof sheeting and paper, windows 10-15

Aug. 29-Sept. 2 Electrical/plumbing rough-ins ,shingle Contracted

 Roof, install furnace .

Sept. 3 (Saturday) Soffit and facia 10

Sept. 7 (Wednesday) Finish Soffit and facia, prep for siding Build Com.

Sept. 10 (Saturday) Siding/insulation Women’s Build (20)

Sept. 17 (Saturday) Complete siding/insulation 10-15

Sept. 19-Sept. 30 Drywall (hanging, taping and texturing) Contracted plus 5

Oct. 3-7 Prime and paint Contracted ?

Oct. 10-15 Carpeting/flooring Contracted

Oct. 15 -22 Install cabinets, doors, trim Build Com.

Oct. 24-28 Final plumbing/electrical Contracted

Oct. 29-Nov. 5 Final detail Build Com.

Nov.7-11 Final cleaning 5-8 volunteers

Nov. 13 DEDICATION?